SNATCHIT

4-Week Engineering Execution Plan

Beta-Ready for Miami Music Week

CONFIDENTIAL

Prepared: March 3, 2026

Deadline: March 22, 2026 (20 calendar days)

Target: Miami Music Week (March 23–29, 2026)

# Reality Check: Where You Are Today

HARD DEADLINE: March 22, 2026. You have 20 calendar days. Not 4 full weeks. Every hour counts.

## Current Codebase Score

Based on a full audit of your React Native + Expo + Supabase codebase, here is where things stand:

| Task | Status | Est. Time | Priority |
| --- | --- | --- | --- |
| Auth (signup, login, session persistence) | WORKING | — | DONE |
| Real-time subscriptions (listings + bids) | WORKING | — | DONE |
| Listing creation with image upload | WORKING | — | DONE |
| Bidding system with triggers | WORKING | — | DONE |
| Buy Now with reservation system | WORKING | — | DONE |
| RPCs (reserve, mark sold, finalize, cancel) | WORKING | — | DONE |
| RLS policies + guard triggers | WORKING | — | DONE |
| Profile management + avatar upload | WORKING | — | DONE |
| Stripe payment sheet (test mode) | BROKEN | 3 days | CRITICAL |
| Stripe webhooks | MISSING | 1 day | CRITICAL |
| JWT validation in edge functions | MISSING | 3 hours | CRITICAL |
| Automated auction finalization (cron) | MISSING | 4 hours | CRITICAL |
| Ticket transfer / delivery flow | MISSING | 2–3 days | CRITICAL |
| Ticket verification system | MISSING | 1–2 days | HIGH |
| Admin dashboard | MISSING | 3–4 days | HIGH |
| Stripe Connect (seller payouts) | MISSING | 2 days | HIGH |
| Push notification sending | PARTIAL | 1 day | HIGH |
| UI polish / font / layout tweaks | TODO | 2–3 days | MEDIUM |

The good news: your core auction mechanics are solid. The RPCs use FOR UPDATE locking, bid validation is trigger-based and atomic, RLS is properly configured with guard triggers preventing state column tampering. This foundation is production-quality.

The bad news: everything between “user wins auction” and “user has their ticket” is missing. Payment is half-built with critical security holes. There is no admin visibility. No ticket delivery. No verification. That entire post-purchase pipeline needs to exist in 20 days.

# Prioritization Framework

With 20 days and a venue partner waiting, here is how every feature stacks up. The question for each item: “If this is broken or missing during Miami Music Week, does the product fail?”

TIER 1 — App Does Not Function Without These

- Fix Stripe integration: JWT validation, idempotency keys, env-based keys, webhook handler. Without this, you cannot safely take money.

- Automated auction finalization: Without a cron/scheduled function, auctions only end when someone manually views the listing. Your venue partner will see auctions stuck in limbo.

- Ticket transfer flow: After payment, the buyer needs to receive their ticket. Even a basic “Seller sends transfer code, buyer confirms receipt” flow is mandatory. This is the core value proposition.

- Stripe webhooks: The only reliable way to confirm payments. Without them, network failures and app crashes mean money taken with no record.

TIER 2 — Venue Partner Will Ask About These

- Admin dashboard (basic): Your venue partner will want to see listings, sales, and payouts. You need at minimum a read-only admin view.

- Seller payouts: You can do manual Stripe transfers for MMW, but you need a clear answer for “when and how do I get paid?”

- Ticket verification: Seller identity verification and ticket authenticity indicators. Even a simple “verified seller” badge controlled via admin is enough for V1.

- Push notifications: When someone gets outbid or wins an auction during a live event, they need to know immediately.

TIER 3 — Polish That Makes It Feel Real

- UI/layout/font refinements: Typography, spacing, color consistency, loading states, error states.

- Refund flow: Handle via Stripe Dashboard manually for MMW. Build the in-app flow later.

- Email receipts: Configure Stripe auto-receipts. No custom email templates needed yet.

- Social auth (Apple/Google login): Nice to have for conversion, but email+password works for beta.

# Stripe: The Fix Sequence

Your Stripe integration scores 28/100 on production readiness. Here is the exact order to bring it to launch-ready, with nothing wasted.

Phase A: Security (Days 1–2)

These must be done before any real money touches the system.

- Fix the publishable key. Remove the malformed concatenated key from src/config/app.ts. Set up EXPO_PUBLIC_STRIPE_PUBLISHABLE_KEY in .env.development (test key) and .env.production (live key). Rotate any exposed keys in Stripe Dashboard. Time: 30 minutes.

- JWT validation in both edge functions. Decode the Authorization header, extract the sub claim, use that as buyer_id. Ignore client-supplied buyer_id entirely. Add the same validation to confirm-payment. Time: 2–3 hours.

- Add idempotency keys. Generate deterministic key from listing_id + buyer_id + mode. Pass as Idempotency-Key header to Stripe. Also query for existing pending payment before creating new PaymentIntent. Time: 1–2 hours.

- Remove stripe_client_secret from DB. Drop the column from payments table. Only return it transiently in the edge function response. Time: 20 minutes.

- Add buyer ≠ seller check. In create-payment-intent, verify buyer_id !== listing.seller_id. Time: 15 minutes.

Phase B: Reliability (Days 3–4)

- Stripe webhook handler. New edge function: stripe-webhook/index.ts. Handle payment_intent.succeeded (update payments table + call mark_listing_sold or complete_auction_payment RPC). Handle payment_intent.payment_failed (update status, release reservation). Verify webhook signature. Time: 4–6 hours.

- Fix DB insert failure handling. If payments insert fails in create-payment-intent, cancel the Stripe PaymentIntent before returning error. Time: 30 minutes.

- Handle payment-succeeded-but-listing-update-failed. In the webhook handler, if the RPC fails, queue a retry (simple: insert into a retries table, check on next webhook). Time: 1–2 hours.

Phase C: Seller Payouts (Days 5–6)

- Stripe Connect onboarding. Create a Connect Express account for your venue partner. Build the onboarding link flow (Stripe handles the KYC). Store the connected account ID in profiles. Time: 4–6 hours.

- Automatic transfers on payment success. In the webhook handler, after marking listing sold, create a Stripe Transfer to the seller’s connected account (minus your platform fee). Time: 2–3 hours.

Safely Defer Until After MMW

- Dispute/chargeback webhook handlers (handle manually via Stripe Dashboard)

- Refund API endpoint (use Stripe Dashboard)

- 3DS/SCA compliance testing (Miami-first, US cards)

- Rate limiting on edge functions (low volume at beta)

- Payment archival/cleanup cron

- Structured logging replacement for console.log

- Fraud detection / Stripe Radar rules

# Ticket Transfer: What to Build

This is the feature that makes SnatchIt a real product versus a demo. After someone pays, they need to actually receive a ticket. Your schema already has transfer_method (mobile_transfer | email) and restrictions fields on listings. Here is the V1 architecture.

## Transfer Flow (V1)

- Seller creates listing and specifies transfer_method (mobile transfer or email).

- Buyer wins auction or completes Buy Now. Payment is confirmed via Stripe webhook.

- System creates a transfer record (new transfers table) with status “pending.”

- Seller receives push notification: “Your [event] ticket sold! Send the transfer now.”

- Seller opens the app, navigates to the transfer screen, and enters the transfer confirmation code or uploads a screenshot of the completed transfer.

- Buyer receives push notification: “Your ticket transfer is ready! Confirm receipt.”

- Buyer confirms receipt in the app. Transfer status moves to “completed.”

- If buyer does not confirm within 24 hours, or disputes the transfer, it escalates to admin (you, manually, for now).

## New Database Objects Needed

- transfers table: id, listing_id, payment_id, seller_id, buyer_id, transfer_method, status (pending | seller_sent | buyer_confirmed | disputed | expired), transfer_code (text), transfer_screenshot_path (storage), seller_sent_at, buyer_confirmed_at, created_at, expires_at.

- RLS: Seller can update their own transfer (add code/screenshot). Buyer can update their own transfer (confirm receipt). Both can read their own transfers.

- RPC: seller_send_transfer (validates seller owns it, updates status + code). buyer_confirm_transfer (validates buyer owns it, updates status).

## New Screens Needed

- TransferSendScreen: Seller sees buyer info, transfer method, and inputs the confirmation code or uploads screenshot. One button: “Mark as Sent.”

- TransferReceiveScreen: Buyer sees transfer details, confirmation code, and two buttons: “Confirm Received” or “Report Issue.”

- TransferStatusBadge: Component shown on listing cards and detail screens showing transfer state.

Estimated total build time: 2–3 days including database, RPCs, screens, and push notifications.

# Admin Dashboard: The Minimum Viable Version

You do not need a full-featured admin portal for MMW. You need enough visibility to operate the platform during live events and enough control to handle problems in real-time.

## Architecture Decision

Build it as a web app, not inside the React Native app. Use Next.js or even a simple React SPA hosted on Vercel. It connects to the same Supabase instance using a service role key. This keeps admin logic completely separate from the consumer app and lets you iterate on it independently.

## V1 Admin Screens (4 screens total)

1. Dashboard Overview

- Active listings count, active auctions count, total GMV, pending transfers

- Recent transactions list (last 24 hours)

- Flagged items (disputed transfers, failed payments)

2. Listings Management

- Table of all listings with filters: status, auction_status, date range

- Actions: view detail, cancel listing, feature/unfeature

- Seller info for each listing

3. Payments & Transfers

- All payments with status filters (pending, succeeded, failed, refunded)

- All transfers with status filters

- Action: manually mark transfer as completed (for disputes you resolve via phone/text)

- Action: trigger refund via Stripe API

4. User Management

- User list with search

- Toggle is_verified_seller and is_verified_buyer flags

- View user’s listings, bids, payments

- Ban/suspend user (add an is_banned flag to profiles, check in RLS)

Estimated build time: 3–4 days for a functional admin panel. Use a UI library like shadcn/ui or Ant Design to move fast. Do not design from scratch.

WEEK 1 FIX WHAT’S BROKEN March 3–9 (Mon–Sun)

This week is purely about closing security holes and making the existing features actually work end-to-end. No new features. No UI changes. Just make it solid.

## Day 1–2: Stripe Security Lockdown

- Fix Stripe publishable key (30 min) — Move to env vars. Remove hardcoded key from source. Set up .env.development with pk_test_ key.

- JWT validation in edge functions (3 hours) — Both create-payment-intent and confirm-payment must decode the JWT, extract user ID from sub claim, ignore client-supplied buyer_id.

- Idempotency keys on PaymentIntent creation (2 hours) — Deterministic key = listing_id:buyer_id:mode. Add duplicate payment check before creating new intent.

- Remove client_secret from payments table (20 min) — Drop column. Return transiently only.

- Add buyer ≠ seller validation (15 min) — Check in create-payment-intent.

## Day 3–4: Stripe Webhooks + Reliability

- Build Stripe webhook edge function (5 hours) — Handle payment_intent.succeeded, payment_intent.payment_failed. Verify webhook signature. Update payments table. Call mark_listing_sold or complete_auction_payment.

- Fix DB insert failure handling (30 min) — Cancel orphaned PaymentIntents if DB insert fails.

- Payment-succeeded-but-RPC-failed recovery (2 hours) — Retry logic in webhook handler.

## Day 5: Auction Automation + Cron

- Deploy auction auto-finalization (3 hours) — Supabase Edge Function or pg_cron calling auto_finalize_expired_auctions() every 60 seconds. The RPC already exists; you just need the scheduler.

- Test complete auction lifecycle (2 hours) — Create listing → place bids → auction ends → auto-finalized → winner determined. Verify in DB.

## Day 6–7: End-to-End QA

- Full Buy Now flow: list → reserve → pay (test mode) → webhook fires → listing marked sold

- Full Auction flow: list → bid → auction ends → auto-finalize → winner pays → sold

- Edge cases: reservation expiry, double-tap payment, back-button release, session expiry mid-payment

- Verify all payments have corresponding DB records

- Verify idempotency (hit pay twice → only one PaymentIntent)

WEEK 1 EXIT CRITERIA: Both payment flows work reliably in test mode. Stripe security is locked down. Auctions auto-finalize. Zero crashes on core flows.

DO NOT WASTE TIME ON THIS WEEK

- UI changes of any kind

- Admin dashboard

- Push notifications

- Ticket transfer flow

- New features

WEEK 2 BUILD THE POST-PURCHASE PIPELINE March 10–16 (Mon–Sun)

Stripe works. Auctions finalize. Now build what happens after someone pays: ticket transfer, seller payouts, and basic verification. This is the week that turns a demo into a product.

## Day 8–9: Ticket Transfer System

- Create transfers table + RLS + RPCs (3 hours) — Schema, policies, seller_send_transfer and buyer_confirm_transfer RPCs with FOR UPDATE locking.

- Wire webhook to create transfer record (1 hour) — On payment_intent.succeeded, after marking listing sold, insert a transfer row with status “pending.”

- Build TransferSendScreen (4 hours) — Seller sees buyer info, enters transfer code or uploads screenshot. Mark as Sent button.

- Build TransferReceiveScreen (3 hours) — Buyer sees transfer details, Confirm Received and Report Issue buttons.

- Add TransferStatusBadge component (1 hour) — Shows on listing cards and detail view.

## Day 10–11: Seller Payouts + Verification

- Stripe Connect Express onboarding (4 hours) — Edge function to create Connect account + onboarding link. Store connected_account_id in profiles. Build a simple “Set Up Payouts” screen in settings.

- Auto-transfer on payment success (2 hours) — In webhook handler, after marking sold, create Stripe Transfer to seller’s connected account minus platform fee.

- Seller verification via admin (1 hour) — Add is_banned boolean to profiles schema. Build the toggle into the admin dashboard (Week 3). For now, manually set is_verified_seller via Supabase Dashboard for your venue partner.

- Verified Seller badge in UI (1 hour) — Show a checkmark badge on listings and profile when is_verified_seller is true.

## Day 12–13: Push Notifications

- Outbid notification (2 hours) — Database trigger on bids INSERT: find previous highest bidder, look up push_token, send via Expo push API.

- Auction won notification (1 hour) — Trigger from finalize_auction: notify winner.

- Transfer notifications (1 hour) — Notify buyer when seller sends transfer. Notify seller when buyer confirms.

- Payment confirmation notification (30 min) — From webhook: notify buyer on payment success.

## Day 14: Integration Testing

- Full lifecycle test: create → bid → win → pay → transfer → confirm

- Push notifications firing at every stage

- Seller payout landing in connected account (test mode)

- Verified seller badge displaying correctly

WEEK 2 EXIT CRITERIA: Complete post-purchase pipeline working. Ticket transfer flow end-to-end. Seller payouts via Stripe Connect. Push notifications on all key events. Verified seller badge visible.

DO NOT WASTE TIME ON THIS WEEK

- Admin dashboard (next week)

- UI redesign

- Email templates

- Social auth

- Watchlist feature

WEEK 3 ADMIN + UI POLISH + GO LIVE March 17–22 (Tue–Sun)

The app works end-to-end. Now build the operational tools you need to run it during MMW, polish the UI so it feels professional, and switch to live Stripe keys.

## Day 15–17: Admin Dashboard

- Set up admin web app (2 hours) — Next.js project on Vercel (or simple React SPA). Connect to Supabase with service role key. Use shadcn/ui or Ant Design for speed.

- Dashboard overview page (3 hours) — Active listings, active auctions, GMV, pending transfers, recent transactions, flagged items.

- Listings management page (3 hours) — Table with filters. View detail. Cancel listing. All listings from all sellers.

- Payments & transfers page (3 hours) — Payment list with status filters. Transfer list. Manual complete/refund actions.

- User management page (2 hours) — User list, search, verify/ban toggles, view user activity.

## Day 18–19: UI Polish

This is where you make it feel like a real product, not a prototype. Focus on the screens your users will see most during MMW.

- Home feed refinement — Card layout, typography, countdown timer styling, image loading states, empty states.

- Listing detail screen — Bid history layout, price display, auction status indicators, CTA button states.

- Checkout flow — Clear price breakdown, fee disclosure, loading states, success/error animations.

- Transfer screens — Clear status indicators, step-by-step instructions, confirmation UI.

- Profile screen — Seller stats, verification badge, payout status.

- Error states everywhere — Network errors, empty states, loading skeletons. No blank screens.

## Day 20: Go Live

- Switch to live Stripe keys. Update .env.production. Deploy edge functions with live keys.

- Run one real transaction end-to-end. Create a real listing. Buy it with a real card. Verify webhook fires. Verify payment shows in Stripe Dashboard. Verify seller payout. Verify transfer flow.

- Verify your venue partner’s Stripe Connect account is live. Complete their KYC if not already done.

- Create your venue partner’s first real listings. Work with them to get event details, photos, and ticket quantities for MMW events.

- Final smoke test. Every flow, one more time, with live keys.

WEEK 3 EXIT CRITERIA: Admin dashboard operational. UI polished and professional. Live Stripe keys enabled. First real listings created for MMW. One successful live transaction completed.

DO NOT WASTE TIME ON THIS WEEK

- New features of any kind

- Refactoring or code cleanup

- Performance optimization

- Analytics integration

- Anything that isn’t user-facing or operationally critical

WEEK 4 MIAMI MUSIC WEEK — WAR ROOM March 23–29 (Mon–Sun)

This is not a development week. This is an operations week. The app is live. Your venue partner has listings. Real users are bidding with real money. Your job is to keep everything running and fix problems in real-time.

## Daily Rhythm

- Morning (9 AM): Check Stripe Dashboard for overnight transactions. Check admin dashboard for flagged items. Verify all auction finalizations ran. Check for any failed webhooks.

- Midday (12 PM): Check transfer statuses. Follow up with sellers who haven’t sent transfers. Follow up with buyers who haven’t confirmed. Resolve any disputes personally.

- Evening (6 PM): Monitor live auctions during peak nightlife hours. Be ready to hotfix. Have your laptop and Stripe Dashboard open.

- Night (10 PM–2 AM): This is when your users are active. Monitor in real-time. Be in the venues if possible. Watch the app being used. Note every friction point.

## Engineering Priorities (Only If Something Breaks)

- Payment failures: highest priority. If webhooks are failing, fix immediately.

- Transfer disputes: second priority. Mediate between buyer and seller directly.

- Push notification failures: third priority. Users missing outbid alerts during live auctions is lost revenue.

- UI bugs: fix only if they block the core flow. Cosmetic issues can wait.

## Data to Collect

- Total GMV processed

- Number of listings sold (Buy Now vs Auction)

- Average auction price vs starting bid (price lift metric)

- Number of unique bidders

- Transfer completion rate and time

- Support issues and categories

- User feedback (talk to people at the events)

WEEK 4 EXIT CRITERIA: Survive Miami Music Week. Process real transactions. Collect real data. Fix what breaks. Document everything for the post-MMW roadmap.

# Risk Register

| Task | Status | Est. Time | Priority |
| --- | --- | --- | --- |
| Stripe account suspended (chargebacks, fraud) | Monitor daily | Ongoing | CRITICAL |
| Webhook failures lose payment records | Alert on failure | Week 1 | CRITICAL |
| Auction finalization cron stops running | Health check | Week 1 | CRITICAL |
| Venue partner tickets are fraudulent | Verify manually | Week 2 | HIGH |
| Seller doesn’t transfer ticket after payment | 24hr auto-escalate | Week 2 | HIGH |
| Double charges from missing idempotency | Idempotency keys | Week 1 | HIGH |
| App Store review delays (if publishing) | Submit early | Week 2 | HIGH |
| Edge function cold starts during peak | Monitor latency | Week 3 | MEDIUM |
| Push notifications not delivering | Test on device | Week 2 | MEDIUM |
| UI bugs during live demo | QA every flow | Week 3 | MEDIUM |

# What to Ignore Until After MMW

These are real features that matter eventually but will eat your time and deliver zero value for the March 23 deadline.

- Social auth (Apple/Google login) — Email + password is fine for beta. Nobody will refuse to sign up because you don’t have Apple Sign-In.

- Watchlist feature — The WatchButton component and types exist but there’s no DB table. Leave it. Not relevant for MMW.

- Legacy code cleanup (dual Auction/Listing data model) — Technical debt that doesn’t affect users. Clean it up in April.

- Structured logging / Sentry integration — Console.log is fine for 20 days. Add proper monitoring after MMW.

- CI/CD pipeline — Deploy manually. You’re one person. A pipeline saves time at scale, not at 1 developer.

- Email templates (receipts, confirmations) — Configure Stripe auto-receipts in Dashboard. That’s enough.

- Dispute resolution automation — You will personally handle every dispute during MMW. Build automation when volume demands it.

- Ratings/reviews system — Not relevant for a beta with one venue partner.

- Chat/messaging between buyer and seller — They can communicate about transfers through the transfer flow. No DMs needed.

- Multi-language support — Miami is bilingual but English-first for the app is fine for beta.

- Analytics dashboard in the consumer app — Sellers don’t need analytics for their first 10 listings.

- CORS restrictions on edge functions — Mobile app. Not relevant.

- Payment amount display mismatch fixes — Stripe PaymentSheet shows the real amount. Good enough.

# 20-Day Engineering Tracker

Pin this to your wall. Check off each item as you complete it. If you fall behind by more than 1 day, cut scope from Week 3 UI polish, not from Weeks 1–2 infrastructure.

| Day | Date | Deliverable | Hours |
| --- | --- | --- | --- |
| 1 | Mar 3 | Stripe key fix + JWT validation (both edge fns) | 4h |
| 2 | Mar 4 | Idempotency keys + remove client_secret + buyer≠seller | 3h |
| 3 | Mar 5 | Stripe webhook handler (payment_intent.succeeded/failed) | 5h |
| 4 | Mar 6 | Webhook reliability: DB failure handling + retry logic | 3h |
| 5 | Mar 7 | Auction auto-finalization cron + test full auction lifecycle | 5h |
| 6 | Mar 8 | End-to-end QA: Buy Now flow (test mode) | 4h |
| 7 | Mar 9 | End-to-end QA: Auction flow + edge cases | 4h |
| 8 | Mar 10 | Transfers table + RLS + RPCs | 4h |
| 9 | Mar 11 | TransferSend + TransferReceive screens | 7h |
| 10 | Mar 12 | Stripe Connect Express onboarding + payout screen | 6h |
| 11 | Mar 13 | Auto-transfer in webhook + verified seller badge | 4h |
| 12 | Mar 14 | Push notifications: outbid + auction won + transfers | 4h |
| 13 | Mar 15 | Push: payment confirmation + full lifecycle integration test | 4h |
| 14 | Mar 16 | Buffer day: catch up on anything behind schedule | 6h |
| 15 | Mar 17 | Admin dashboard: setup + overview page | 5h |
| 16 | Mar 18 | Admin: listings management + payments/transfers pages | 6h |
| 17 | Mar 19 | Admin: user management + final admin QA | 4h |
| 18 | Mar 20 | UI polish: home feed, listing detail, checkout flow | 6h |
| 19 | Mar 21 | UI polish: transfers, profile, error states + loading states | 6h |
| 20 | Mar 22 | GO LIVE: switch to live keys, real transaction, smoke test | 4h |

Total estimated engineering hours: ~93 hours over 20 days

That is roughly 5 hours/day of focused engineering.

Aggressive but achievable for a solo founder who knows the codebase.

# Final Word

You have a venue partner. You have a working auction engine. You have 20 days and the biggest nightlife week in Miami as your launchpad. That is a rare alignment of timing and opportunity.

The plan above is tight but achievable. The key discipline is this: do not deviate. Do not add features that are not on this list. Do not redesign screens that work. Do not optimize code that runs. Every hour you spend on something not in the 20-day tracker is an hour stolen from something that matters.

Week 1 makes the payments safe. Week 2 makes the product complete. Week 3 makes it polished and live. Week 4 is the test. If you execute this, you walk out of Miami Music Week with real GMV, real users, real data, and a real story to tell investors and venue partners.

Ship the V1. Run it during MMW. Learn everything. Build the V2 with data, not guesses.